## Summary
4 Systems: | Carrefour, Tesco, YongHui, Metro
Phase | Effort | Distribution
Development | 28 | 87.5%
Test | 4 | 12.5%
Total | 36
7 Systems: | 58
Effort
58

## Common
Function | Qty | Effort (MD) | Total Effort | Remark
Framework | 1 | 3 | 3 | Configuration: Customer indicator, Site info, User info(disable indicator), Date, thread, File path
Multi-thread | 1 | 3 | 3
File Merge Process | 4 | 0.5 | 2 | The effort will be increased for new cumstomer
System customize for each retailer | 4 | 0.5 | 2
汇总 |  | 7 | 10

## Sheet1
Effort Summary
Common
Function | Qty | Effort (MD) | Total Effort | Remark
Framework | 1 | 3 | 3 | Configuration: Customer indicator, Site info, User info(disable indicator), Date, thread, File path
Multi-thread | 1 | 3 | 3
Total |  | 6 | 6
Carrefour
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1
Order Process | 1 | 2 | 2
Receiving Note Process | 1 | 1.5 | 1.5 | Excel Process
File Merge Process | 1 | 1 | 1 | 1. Matching 2. Merge File
System Configuration | 1 | 0.5 | 0.5
Sub Total |  | 6 | 6
Tesco
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order Process | 1 | 2.5 | 2.5 | Javascript Pagination
Receiving Note Process | 1 | 1.5 | 1.5 | Excel Process
File Merge Process | 1 | 1 | 1 | 1. Matching 2. Merge File
System Configuration | 1 | 0.5 | 0.5
Sub Total |  | 6.5 | 6.5
YongHui
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order Process | 1 | 1.5 | 1.5 | Javascript Pagination
Receiving Note Process | 1 | 2 | 2
File Merge Process | 1 | 1 | 1 | 1. Matching 2. Merge File
System Configuration | 1 | 0.5 | 0.5
Sub Total |  | 6 | 6
Metro
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order Process | 1 | 1.5 | 1.5 | Javascript Pagination
Receiving Note Process | 1 | 2 | 2
File Merge Process | 1 | 1 | 1 | 1. Matching 2. Merge File
System Configuration | 1 | 0.5 | 0.5
Sub Total |  | 6 | 6
Others
Function | Qty | Effort (MD) | Total Effort | Remark
Testing | 4 | 1.5 | 6
Warranty | 1 | 2 | 2
User Manual | 1 | 1 | 1
Sub Total |  | 4.5 | 9
Total |  |  | 39.5

## Carrefour
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1
Order | 1 | 2 | 2
Receiving Note | 1 | 1 | 1
Convert Excel to txt file - Receiving Note | 1 | 0.5 | 0.5
汇总 |  | 4.5 | 4.5

## Tesco
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order | 1 | 2.5 | 2.5 | Javascript Pagination
Receiving Note | 1 | 1 | 1
Convert Excel to txt file - Receiving Note | 1 | 0.5 | 0.5
汇总 |  | 5 | 5

## YongHui
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order | 1 | 1 | 1 | Javascript Pagination
Receiving Note | 1 | 1.5 | 1.5
Convert Excel to txt file - Receiving Note | 1 | 0.5 | 0.5
汇总 |  | 4 | 4

## Metro
Function | Qty | Effort (MD) | Total Effort | Remark
Login Validation | 1 | 1 | 1 | HTTPS
Order | 1 | 1.5 | 1.5 | Javascript Pagination
Receiving Note | 1 | 1.5 | 1.5
Convert Excel to txt file - Receiving Note | 1 | 0.5 | 0.5
汇总 |  | 4.5 | 4.5